## Sheet4
Phase | Activity | in weeks | Planned completion
MVP | fix the existing code , and make it SOLID | 2 | 2024-04-29
MVP | add the authetication function | 1 | 2024-05-06
MVP | add the audit ffunction | 1 | 2024-05-13
MVP | add the nested comment feature | 1 | 2024-05-20
MVP | add the file upload function | 1 | 2024-05-27
MVP | add another 20 tables | 6 | 2024-07-08
MVP | Deployment (Docker) and demo | 2 | 2024-07-22
MVP | buffer 60% | 8.4 | 2024-09-18 19:12
Phase2 | Build LLM integration with RAG for Narrative reporting | 2 | 2024-10-02 19:12
Phase3 | LLM to take unstructured data and load in tables | 2 | 2024-10-16 19:12
Phase4 | Check scale and performance improvemeents for million records | 6 | 2024-11-27 19:12
2024-11-27 19:12
Formulas:
Planned completion = TODAY()+(7*SUM(D3:[in weeks]))